## Backend
PROJECT TRACKING CSI 495
|  |  |  | PROJECT TITLE: KeeperAI BACKEND |  |  | DELIVERABLE(S) |  | HOURS
AT RISK | STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | DELIVERABLE | % DONE |  | ESTIMATED HOURS | ACTUAL HOURS | STATUS KEY | PRIORITY KEY
2024-04-10 | In Progress | High | 2024-09-13 | Models/Routes, Controllers Complete | Fully fleshed out and operable base API and CRUD operations for front-end interaction. Some AI integration | Hoki | a simple functioning back-end to test dynamics of front end | 32% |  | 7 |  | Not Started | High
| In Progress | High | 2024-09-16 | Full MVC architecture defined. AI Integration into every API endpoint | Dynamic end-to-end interaction with AI integrated into API calls and operations | Hoki | interactive web app |  |  | 7 |  | In Progress | Medium
| Not Started | Medium | 2024-09-16 | Record Demo of POSTMAN API operations for presentation | Adding someting more interesting to our presentation and showcases progress |  | Insightful demo video |  |  | 1 |  | Overdue
| Not Started | Medium | 2024-09-21 | Rebalancing for security and user administration | Focusing on more than just basic functional qualities |  | More secure, user oriented back-end |  |  | 7
| Not Started | Medium | 2024-09-16 | Alter Schema for Books table and other tables to store all information needed for books | Books table needs pubished date, rating, description, and cover added. Look into adding a shelf table so books are associated with a "shelf" | Etnan | Finished book table, and possibly shelf table |  |  | 3 |  | Complete | Low
Overdue
| Not Started | High

## Frontend
PROJECT TRACKING CSI 495
|  |  |  | PROJECT TITLE: KeeperAI FRONTEND |  |  | DELIVERABLE(S) |  | HOURS
AT RISK | STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | DELIVERABLE | % DONE |  | ESTIMATED HOURS | ACTUAL HOURS | STATUS KEY | PRIORITY KEY
| In Progress | High | 2024-09-16 | main page basic functionality | User friendly and visually pleasing mainpage | diego | working/accessible main page | 60% |  | 8 |  | Not Started | High
| Not Started | Low | 2024-09-18 | sub pages available | User can access other available pages |  | pages outside of the main page |  |  | 6 |  | In Progress | Medium
| Not Started | High | 2024-09-23 | Interface interactive | Interface interactive accessibility and manipulate items in page and get visuals |  | User can upload images |  |  | 6 |  | Complete | Low
| Not Started | High | [9 empty] | On Hold
Overdue

## AI
PROJECT TRACKING CSI 495
|  |  |  | PROJECT TITLE: KeeperAI AI STATS |  |  | DELIVERABLE(S) |  | HOURS
AT RISK | STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | DELIVERABLE | % DONE |  | ESTIMATED HOURS | ACTUAL HOURS | STATUS KEY | PRIORITY KEY
| In Progress | Low | 2024-09-24 | Finish Initial Tests with ChatGPT | Test 5 photos using ChatGPT | Logan | Test Results have been found for other photos | 40% |  | 2 |  | Not Started | High
2024-03-10 | In Progress | Medium |  | Testing AI Models | Test AI models for accuracy, look for errors | Logan | Useful Data about the AI models |  |  |  |  | In Progress | Medium
| Not Started | Medium | 2024-09-30 | Do testing with premium AI APIs | Test photos using the high end models. Will need to use the APIs for this as using the websites requires you to pay for a subscription. | [6 empty] | Complete | Low
On Hold
Overdue

## Misc
PROJECT TRACKING CSI 495
|  |  |  | PROJECT TITLE: |  |  | DELIVERABLE(S) |  | HOURS
AT RISK | STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | DELIVERABLE | % DONE |  | ESTIMATED HOURS | ACTUAL HOURS | STATUS KEY | PRIORITY KEY
[12 empty] | Not Started | High
[12 empty] | In Progress | Medium
[12 empty] | Complete | Low
On Hold
Overdue